# SAHANA — Unified Climate Risk & Travel Intelligence Platform for Sri Lanka

### Combined Project Scope: DIWASA + SriSafe AI

### CIS047-3 Agile Project Management — 10-Week Group Project Specification (Team of 5)

## 0. What This Document Is

This is the master scope for the merged project. "SAHANA" (Sinhala: comfort/relief/safety) is the umbrella platform name. It has one shared intelligence core and two front-facing modes:

- SriSafe Mode — for tourists: "where should I go, and when?"

- DIWASA Mode — for residents/authorities: "how risky is this area right now?"

Both modes are powered by the same Core Risk Engine, trained on the same historical datasets. This is the central design decision of the whole project, and it's worth understanding why before anything else.

## 1. Why the Merge — The Strategic Case (use this for your "alternatives considered" discussion)

Your reflective report's "Discussion" criterion (20%) rewards showing you considered alternatives and understood the consequences of each. Here are the three strategies your team should document as having been weighed:

Strategy A — Build DIWASA in full. Pros: maximum "wow factor," directly tied to a real disaster (Cyclone Ditwah, Nov 2025, 643+ deaths, 2.3M affected — verified, not exaggerated). Cons: requires live API ingestion, a fine-tuned multilingual NLP model (research-grade work for Sinhala/Tamil), SMS/WhatsApp dispatch infrastructure, and an evacuation-routing engine — realistically 6+ months of specialist work, not 10 weeks part-time for 5 undergrads. High risk of having nothing working for the demo video. Also carries a real ethical issue: presenting a student prototype as a life-safety system risks false confidence in something unvalidated.

Strategy B — Build SriSafe in full. Pros: low technical risk, achievable, low stakes if the model is wrong. Cons: loses almost all the rich legal/social/ethical material (25% of your grade) that DIWASA's framing provides — a "where to go on holiday" app has comparatively thin ethical stakes.

Strategy C — Merge: shared Core Risk Engine, two modes (chosen approach). Pros: reuses the same ML model and dataset pipeline for both outputs, so technical effort isn't duplicated. The tourism mode becomes your guaranteed deliverable (no live infrastructure needed), while the risk mode becomes your demo differentiator (validated against real Ditwah data, with the multilingual/ethical depth intact at a reduced but real scope — translated UI strings and alert templates rather than a fine-tuned NLP model). Cons: requires discipline to not let the risk mode creep back toward "production disaster system" — must stay framed as "advisory, prototype, illustrative."

Document this reasoning explicitly. It's the single highest-value paragraph you can put in your individual reflective reports, because it directly answers "what alternatives did you consider and what were the consequences of each."

## 2. Problem Statement (Combined)

Sri Lanka has decades of historical climate, disaster, and tourism data scattered across separate, disconnected sources (CHIRPS rainfall archives, NBRO landslide records, DMC disaster reports, SLTDA tourism statistics). Two very different groups of people are poorly served by this fragmentation:

- Tourists must manually cross-reference multiple websites to figure out when and where it's safe and pleasant to travel.

- Residents and local authorities — as Cyclone Ditwah brutally demonstrated in November 2025 — often receive risk information too late, in the wrong language, or not at all, because warning systems are siloed across five separate agencies (DMC, Met Dept, Irrigation Dept, NBRO, Police).

SAHANA's thesis: the same historical data, run through one risk-scoring model, can answer both "is this a good time to visit?" and "is this area currently risky?" — the only difference is the lens applied to the output.

## 3. Goals & Success Criteria (MVP / Stretch / Roadmap)

Structuring goals into three tiers is itself good Agile practice (and gives you a natural "what we achieved vs. what we'd do with more time" narrative for the Project Manager's lessons-learned report).

### MVP — must deliver by Week 10

- Core Risk Engine: ML model producing flood risk, landslide risk, and weather-comfort scores per district, per month, from historical data

- SriSafe Mode: month + interest input → ranked destination recommendations with safety/comfort scores

- DIWASA Mode: district-level risk map (Green/Amber/Red/Black tiers) based on historical/seasonal patterns

- "Ditwah Replay" — feed the model Oct/early-Nov 2025 data and show it would have flagged the districts that were actually worst-hit (Kandy, Gampaha, Colombo, Nuwara Eliya, Puttalam)

- Sinhala / Tamil / English UI strings and alert templates (translated, native-speaker-reviewed — not ML-generated)

- Full PM documentation suite (all five roles)

- 5-minute demo video

### Stretch — only if MVP is ahead of schedule

- Near-real-time risk updates via NASA GPM API (instead of purely historical/seasonal)

- LSTM time-series layer for short-term forecasting on top of the XGBoost baseline

- Text-only "community report" submission form (no ML classification — just stored and displayed)

- "SMS alert preview" — shows what an SMS would say, without actually sending one (keeps the demo realistic without needing a live Twilio account or making real dispatch claims)

### Roadmap — explicitly not built this module, documented as future vision

- Fine-tuned mBERT/IndicBERT for nuanced Sinhala/Tamil alert generation

- Live evacuation routing (OSMnx + Dijkstra)

- Formal NBRO/DMC/Met Dept API partnerships and data-sharing agreements

- WhatsApp Business API / SMS dispatch infrastructure

- Crowdsourced report verification (image + text classifier)

- Government liaison for official alert-issuing authority

Putting the roadmap in writing (rather than pretending the MVP is the production system) is what lets you honestly claim "this is production-track" without overclaiming what a 10-week student prototype actually is.

## 4. System Architecture

┌─────────────────────────────────────────────────────────────┐
│                      DATA LAYER (Supabase/Postgres)            │
│  CHIRPS rainfall · NBRO landslide records · DMC disaster log   │
│  UNOSAT flood maps · GADM boundaries · SLTDA tourism stats      │
│  Curated activity-season reference table (surf/whale/hiking)   │
└───────────────────────────┬───────────────────────────────────┘
                             │
┌───────────────────────────▼───────────────────────────────────┐
│              CORE RISK ENGINE (FastAPI + ML, Colab-trained)     │
│  Model 1: Risk Scoring Model (XGBoost/LightGBM)                 │
│   → flood risk / landslide risk / comfort score per             │
│     district per month                                          │
│  Model 2: Recommendation Scorer (rule-based, uses Model 1's     │
│     outputs + interest-activity matrix)                         │
└─────────┬─────────────────────────────────────┬─────────────────┘
          │                                       │
┌─────────▼─────────────┐           ┌────────────▼─────────────────┐
│   SriSafe Mode          │           │   DIWASA Mode                  │
│   (Flutter, primary)    │           │   (Flutter tab / web dashboard)│
│  - Trip planner          │          │  - District risk map           │
│  - Destination recs      │          │  - Ditwah replay view           │
│  - Safety/comfort scores │          │  - Multilingual alert templates │
│  - Map view              │          │  - (Stretch) SMS preview         │
└──────────────────────────┘           └─────────────────────────────┘

Both modes call the same FastAPI endpoints (/risk-score, /recommendations) — this is the technical embodiment of "one engine, two faces" and is the cleanest thing to point at in your architecture diagram when explaining the merge decision.

## 5. Data Sources — Detailed

| Source | What it gives you | Access | Used for |
| --- | --- | --- | --- |
| CHIRPS Rainfall (1981–2025) | Satellite + gauge rainfall, sub-district level | Free, HDX (data.humdata.org) | Core Risk Engine — flood risk training data |
| NBRO Landslide Records + Rain Gauges | 10+ years of landslide events with GPS, severity | Free / contact for full API | Core Risk Engine — landslide risk training data |
| UNOSAT Flood Geospatial Maps | GeoJSON flood extent for Ditwah and 2024 floods | Free, HDX | Ditwah Replay validation |
| DMC Historical Disaster Records (2004–2025) | Per-event deaths, displacement, district impact | Public | Ground truth for model evaluation |
| GADM Admin Boundaries / OpenStreetMap | District/GN boundaries, road network, elevation | Free | Map rendering, terrain features |
| SLTDA Monthly Tourist Arrival Statistics | National-level seasonal visitor patterns | Public | Crowd-level estimation (national trend only — be upfront this isn't destination-granular) |
| Curated Activity-Season Table | Surf season (Arugam Bay Apr–Oct), whale watching (Mirissa Nov–Apr, Trincomalee May–Oct), hiking, cultural sites | You build this manually — small spreadsheet, ~30–50 rows, sourced from tourism board guides and cross-checked | SriSafe recommendation matching |

Note on the curated table: there's no public API for "best month to surf at X beach." This is genuinely your team's own knowledge-engineering work — assign it to whoever has the Quality Manager role, since validating these entries against multiple sources is itself a quality-assurance task worth documenting.

## 6. AI/ML Models — Realistically Scoped for 10 Weeks

### Model 1: Core Risk Scoring Model (the heart of the project)

- Type: Gradient-boosted trees (XGBoost or LightGBM) — not an LSTM ensemble. One well-validated model beats three half-finished ones.

- Input features (per district, per month): average/total rainfall (CHIRPS), historical landslide event count (NBRO), historical flood event count and severity (DMC), elevation/slope summary (GADM/DEM), month-of-year (seasonality).

- Output: flood risk (0–100), landslide risk (0–100), weather-comfort score (0–100), combined into a tier (Green/Amber/Red/Black).

- Validation — the Ditwah Replay: feed the model rainfall data from late October/early November 2025 and check whether it assigns elevated risk to Kandy, Gampaha, Colombo, Nuwara Eliya, and Puttalam — the districts that the DMC confirmed were hardest hit. This is your single most powerful demo moment and your Quality Manager's primary evaluation metric (precision/recall against the actual Ditwah outcome).

### Model 2: Seasonal Recommendation Scorer

- Type: rule-based weighted scoring, not a separate trained ML model — it consumes Model 1's outputs as inputs.

- Formula sketch: suitability_score = (interest_activity_seasonal_fit × 0.4) + ((100 − flood_risk) × 0.25) + ((100 − landslide_risk) × 0.15) + (comfort_score × 0.2)

- Being explicit that this is "AI-assisted scoring built on a trained risk model" rather than claiming a second deep model is more honest and ties directly into the ethical theme of not overstating AI capability.

### Stretch Model 3: LSTM Time-Series Layer

Only attempt this if Model 1 is validated and stable by end of Sprint 4 (Week 4). If attempted, frame it as "augments Model 1's monthly view with a short-term trend signal" — not a replacement.

### Multilingual Support (Sinhala/Tamil/English)

- MVP approach: a fixed set of ~30–40 UI strings and alert-template sentences, translated by a native speaker on the team (or via translation tool + native-speaker review — document this review step for your Quality Manager's plan).

- Explicitly not a fine-tuned mBERT model for the MVP — that's roadmap. This keeps the "language equity" ethical point intact (Ditwah's Tamil-warning delay is directly addressed) without taking on a research-grade NLP task.

## 7. Feature Specification by Mode

### 7.1 SriSafe Mode (Tourist-facing, primary deliverable)

- Onboarding: select travel month(s) and interests (surfing, wildlife/whale watching, hiking, beaches, cultural tourism)

- Ranked destination recommendations with a "Travel Suitability Score"

- Destination detail page: risk breakdown (flood/landslide/comfort), best-months chart, activity notes (e.g. "Arugam Bay surf season runs April–October")

- Interactive map with colour-coded destination markers

### 7.2 DIWASA Mode (Resident/authority-facing, demo differentiator)

- District-level risk map (Green/Amber/Red/Black, based on historical/seasonal model output — labelled clearly as "illustrative, based on historical patterns")

- Language toggle (Sinhala/Tamil/English) affecting risk-tier labels and alert template text

- Ditwah Replay view — side-by-side of "what our model predicts" vs. "what actually happened in Nov 2025"

- Stretch: SMS alert preview panel (text only, never actually dispatched)

### 7.3 Shared Core

- District/region selector synced across both modes

- A persistent, visible disclaimer: "SAHANA is a student prototype for educational purposes. Risk scores are illustrative and based on historical data — they are not official warnings. For real emergencies, follow guidance from the Disaster Management Centre (DMC) and local authorities." — put this on every risk-related screen. It's a one-line addition that does a lot of ethical work.

## 8. Technology Stack

| Layer | Choice | Why |
| --- | --- | --- |
| Mobile app | React Native |  |
| Backend API | FastAPI (Python) | Serves model predictions and recommendation logic; pairs naturally with Colab-trained models |
| ML training | Google Colab | Free GPU access, easy to share notebooks across the team |
| Database | Supabase/Postgres | Free tier, good fit if you've already worked with Supabase schemas before |
| Map rendering | OpenStreetMap / flutter_map | Free, no API key hassle |
| Hosting (backend) | Railway or Render free tier | Simple FastAPI deployment for demo purposes |
| PM tooling | GitHub + Trello/Jira | Kanban board for Scheduling Manager, issue tracking for contribution evidence |

## 9. 10-Week Agile Sprint Plan

| Sprint | Weeks | Goal | Key Tasks | Sprint Review Output |
| --- | --- | --- | --- | --- |
| 1–2 | 1–2 | Foundation & Data | Form team, assign 5 roles; project charter + team code of conduct (BCS-derived); set up GitHub + Trello; download CHIRPS/NBRO/DMC datasets; curate activity-season table | Present charter, roles, data sources to tutor |
| 3–4 | 3–4 | Core Risk Model v1 | Clean/merge datasets into Postgres schema; feature engineering; train Model 1 (XGBoost) on Colab; run Ditwah Replay validation; draft quality plan with eval metrics | Demo Ditwah Replay result; show evaluation metrics |
| 5–6 | 5–6 | SriSafe Mode build | Recommendation scorer logic; Flutter app skeleton + onboarding flow; FastAPI endpoints (/risk-score, /recommendations); connect frontend to backend | Working trip-planner demo |
| 7–8 | 7–8 | DIWASA Mode + multilingual | District risk map UI; Sinhala/Tamil/English string translation + i18n setup; Ditwah Replay view; (if ahead) attempt live NASA GPM integration | Working risk-map demo with language toggle |
| 9–10 | 9–10 | Integration, QA, demo | End-to-end testing; accessibility pass (colour contrast on risk tiers, screen-reader labels); bug fixes; script and record 5-min demo video; finalise all documentation | Final sprint review + demo video |

## 10. Role Assignments & Documentation Map

| Role | Core Documents | Specific Tasks Tied to This Project |
| --- | --- | --- |
| Start-up Manager | Project plan/outline, team code of conduct (BCS-derived) | Define the "shared core, two modes" structure as the official project scope; write the code of conduct with specific clauses on data handling (since you're working with disaster-related data) |
| Project Manager | Lessons-learned report, 5-min demo video | Owns the Strategy A/B/C merge-decision narrative (Section 1) as the centrepiece of the lessons-learned report; scripts and produces the demo video |
| Quality Manager | Quality plan | Defines Model 1's evaluation metrics (precision/recall on Ditwah Replay); owns the translation-review process for Sinhala/Tamil strings; runs accessibility checks |
| Risk Manager | Risk management plan + risk log | Owns the risk register (Section 11) including the scope-descope decision itself as a logged and mitigated risk; tracks data-access risks (NBRO contact delays etc.) |
| Scheduling Manager | Gantt/Kanban, communication plan, meeting minutes | Maintains the Trello board against the sprint table above; schedules weekly standups; archives meeting minutes |

## 11. Risk Register

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Original DIWASA scope too large for 10 weeks | High (if unmitigated) | High — risk of nothing demoable | Mitigated by the merge decision itself — shared core + SriSafe as guaranteed deliverable. Document this as your primary risk-management success story. |
| NBRO data access delayed/restricted | Medium | Medium | Use publicly available HDX datasets (CHIRPS, UNOSAT, DMC) as primary sources; treat NBRO API as enhancement only |
| Overclaiming AI capability in demo/docs | Medium | High (ethical) | Persistent "illustrative, not an official warning" disclaimer on all risk screens; frame Model 2 honestly as rule-based scoring on top of Model 1 |
| Uneven team contribution | Medium | High (individual grades) | Trello task assignment with named owners per card; weekly standups logged in meeting minutes |
| Historical data gaps for some districts | Medium | Medium | Cross-validate CHIRPS against DMC records; document known coverage gaps as a limitation rather than hiding them |
| Multilingual strings inaccurate/culturally off | Low–Medium | Medium (social/ethical) | Native-speaker review step built into Quality Manager's plan before any UI text is finalised |

## 12. Demo Video Plan (5 minutes max)

- 0:00–0:30 — Problem framing: Cyclone Ditwah stats + the fragmented-information problem for tourists

- 0:30–1:30 — SriSafe Mode walkthrough: select month + interest, get ranked recommendations

- 1:30–2:30 — DIWASA Mode walkthrough: district risk map, language toggle

- 2:30–3:30 — Ditwah Replay: model predictions vs. actual Nov 2025 outcomes — your strongest evidence of technical substance

- 3:30–4:30 — Quick architecture overview: "one Core Risk Engine, two modes"

- 4:30–5:00 — Roadmap: what production would require, and why you scoped the MVP the way you did

## 13. Production Roadmap (Beyond the Module — for context, not assessment)

If this genuinely continued past the module, the realistic path to "production" would involve: formal data-sharing agreements with NBRO/DMC/Met Dept, fine-tuned in-language NLP for Sinhala/Tamil (a research collaboration, not a sprint task), live API ingestion with proper uptime guarantees, SMS/WhatsApp dispatch infrastructure with telecom partnerships, an accessibility certification pass, a security/privacy audit (especially if any user accounts or location tracking were added), and — critically — sign-off from an actual disaster-management authority before any output could be presented as more than "illustrative." None of this belongs in the 10-week deliverable, but having it written down shows you understand the gap between "prototype" and "production," which is itself part of demonstrating PM maturity.

## 14. Week 1 Checklist

- ☐ Form group of 5, assign the five roles

- ☐ Set up GitHub repo + Trello board

- ☐ First team meeting: agree on the merge strategy (Section 1) as your documented decision

- ☐ Start-up Manager drafts project charter referencing this scope document

- ☐ Begin downloading CHIRPS, NBRO, DMC, UNOSAT datasets from HDX

- ☐ Start the activity-season reference spreadsheet (even a rough first pass)

- ☐ Schedule weekly standup time that works for all 5 members